## Sheet1
TASK TEMPLATE 1 FOR: Sales Promotion – Microsite Based, Sales Promotions (SMS/SMS+Online/Bill Upload/2 Step Bill Upload)
Process | Task Name | Task Type | Created by | Approvals If any | Zoho Requirement (Feature Wishlist for upgraded version of Zoho) | Task Description (Checklist and what to do under each Task Type) | Exception Scearios (If Any) | SPOC for Exception Request
Campaign Set-Up
Standard Process | Code Generation request | Automatic | Auto | Prashant | OB details entered by Prashant confirming Digits of Code Generation Type etc will be auto -populated in this task decription and shared with team to tak next action. Checklist of manual code validation, record keeping etc to be made in the task for Khaleel to update and seek approval from Prashant. Once approved on Zoho codes to be shared with CS Team. | SO No., Number of codes, Steps to Redeem(Captured automatically from campaign Type), Go Live Date, End Date, Code Bifurcation as per denomination, Number of digits for Codes, Any Special Request(OB level/ Campaign Intiation Level) | Exception - Any change in Digits, Number of codes and bifurcation to be flagged off immeditely as Red Flag Unique Code Generation Request can be received in Advance for on-pack Printing purposes. | Khaleel (Ops)
Standard Process | QR code Generation request | Manual | CSM | Kalyan | Simple Task raise and close | URL for the campaign for re-routing, CSM To ensure they scan the QR Code and vlaidate the linking is done correctly before sharing with the client. (Tiny URL not to be used till Further notice). | Incase URL is not finalised, Dummy Link to client product website (Exception 1) | Sachin (Tech Team)
Standard Process | On-Pack Creative Approval | Automatic | Auto | CS Heads | Pre-filled checklist to auto populate checking parameters like: Validate Promo Communication, Dates, T&C, steps to Redeem, URL, and any Number mentioned for Helpdesk/Missed calls etc. | CSM To validate basis checklist and submit final copy for approval with any additional comments for CS Heads. | No exceptions | CS Heads
Standard Process | Voucher/ Sticker Creatives for the campaign | Automatic | CSM | CS Heads/Prashant | Zoho to Auto-populate checklist for CS things to check in the creative with Creative Brief format in downloadable format in the task itself. | CSM to Validate if we have estimated the Creative and Production cost of any priniting materails via Estimate/Sales team before comitting any deliveries to the client. | Exception wherein client has requested waive off or including printing material in the estimate to be backed by Prashant's approval on email. | Prashant Mittal
Standard Process | Print Quotation + Timeline | Manual | CSM | CS Heads | Simple Task raise and close | ONLY incase printing is done by Bigcity. Timeline and costing to be shared by CSM on email with CS Heads. In case of any major deviation from estimate Prashant to be loopedin.
Standard Process | Print Quotation Approval + Client costing | Manual | CSM | Prashant | Simple Task raise and close | SO no., Number of Voucher/stickers, Printer Cost, Delivery locations everything to be accounted for while raising Invoice for Printing and delivery . | Estimate to be checked on inclusions before committing anything to client.
Standard Process | Terms and conditions (Website) | Automatic | Auto | Prashant | Zoho to Auto-populate the T&C shared in Estimate from Zoho CRM in Editable format for CSM to compile and start working on the same. | 1) Go live Date, Steps to redeem, Duration of the campaign, Cap limit. 2) Glossary to have detailed T&C available for CSM To complete the task at their end, edit promo details and share final version for approvals. | Any deviation requested or change requested in existing T&C to be discssed internally. Any such requests to be closed in -2 day TAT from receipt. | Prashant Mittal /Sales SPOC
Standard Process | Terms and conditions for voucher/sticker | Automatic | Auto | CS Heads | Zoho to auto-populate what all to be taken care of while taking Printing requirement: 1) Content and Creative approvals from client mandatory. 2) Printing cost internal approvals to be taken before assigning the job to vendor. 3) Printing Sample to be shared with client and self before mass printing. | 1) Go live Date, Steps to redeem, Duration of the campaign, Cap limit 2) To check all details going in print are correct no unnecessary punctuation is used anywhere. | Any exception request pertaining to expediting printing or creative to be checked intrenally before committing. Estimate time for Content Development, Creative Development, Sample, Mass Printing and Dispatch before proceeding. | CS Heads
Standard Process | Third Party Partner Approvals | Automatic | Auto | Partner Approval Emails | Simple Task raise and close | No printing can be initiated and approved, without partner approvals specially where logo is used. Inform client on the same with TAT's on email. | Only exception is where generic names are used instaed of logos. Example. Food Coupons instead of Swiggy/Zomato. | Amit/Prashant
Standard Process | Server Request | Automatic | Auto | Prashant | Prompt to Prashant to advise Type of Server required (Dedicated/Shared) etc. Operations team to seek approvals if any and raise requests with vendor for the same. | CSM to ensure that Server Task is closed withing 24-48 Hours from assigning, after which it will be marked as Red Flag and will feature as Dealyed Task to owner. | In case of non-receipt of server within defined timeline, Ops to move to Vendor 2 for fulfilment. | Khaleel (Ops)
Standard Process | Microsite Setup | Automatic | Auto | CS Heads | Pre-filed checklist of what all to take care of in the campaign (As shared in Sheet 2 here) | CSM to share: Domain Name, Steps to redeem, Cap limit, Website Banner, FAQs, Thankyou page message(if needs to be customised), Terms and conditions, Go Live Date, End Date | Purchasing specific Domain requires go ahead from Prashant and JD to initiate blocking of desired URL from go Daddy. | Tech Person Assigned In this campaign type it will be Khaleel.
Standard Process | Procurement | Automatic | CSM | CS Heads/Prashant | Special Approval (Commercials/Timelines) that Amit/Mousumi would want under this task can feature as Sub Task and can be assigned for Prashant to approve or suggest way forward. | Procurement can only be done when we receive 100% advance against Rewards to be procurred. A timeline of 3-4 working days for EGV's and 7-8 working days for physical item procurement can be shared with client once our Finnace team approves payment receipt on the same. | Exceptions in case of unavailability of Brand EGV's and Items to be cross checked with next available item and take clients written approval before procurement. | Prashant Mittal
Testing and Go live Readiness
Standard Process | Microsite Testing - Internal | Automatic | Auto | CS Heads | Checklist scenarios Document to be shared in Task Type for CSM Use (If Required to share Testing Results - Internaly or with the client). | Testing Checklist to be followed - Major Points -Formatting need to be correct, TNC dates, Cap limit, Steps to Redeem, FAQs as approved. | No exceptions | CS Heads
Standard Process | Microsite Testing - Client | Automatic | CSM | CS Heads | Checklist scenarios Document to be shared in Task Type for CSM Use (If Required to share Testing Results - Internaly or with the client). | Client Approval required on Testing in the form of Go Live Deck (explained ahead). Extra codes for cleint testing should be taken from Ops team. | No exceptions | NA
Standard Process | Final Campaign Mail | Automatic | Auto | NA | Data fields for this to be picked from the OB Related to the Project and CSM Can trigger getting pre-filled checklist for First Campaign Mail from Zoho itself on their emailUD's. | Final Campaign Mail - Template to be followed CSM can make further edits to FCM Triggered from system and share to respective stakeholders with Campaign Creatives. | No exceptions | NA
Standard Process | GO Live Deck | Automatic | Auto | CS Heads/Client | Simple Task raise and close with reminder to complete this activty before Go live. | CSM's to add few slides only in Campaign Initiation Deck with screen wise flow along with Test codes etc for final approvals from client on the flow and testing and website look and feel. | No exceptions | NA
Standard Process | Operations Team Briefing | Automatic | Auto | NA | All relevant promo details to be automatically published to Opeartions team as and when the task is updated by CSM. | Go live deck with website flow and specifying interventions required from Ops team if any to be added and shared during the internal briefing call. To be done prior to Campaign Go -Live. | No exceptions | NA
Standard Process | MIS - As per predefined Frequency | Automatic | Auto | Prashant | Simple task raise and complete. | Details to be checked - Number of codes, Start Date, End Date, Redemption Requests. CS Heads to approve specimen copy of MIS and ensure client is informed on Frequency. | Exception in terms of what all data pointers can be shared with the client to be shared as High Priorty Task to be flagged of to CS Heads/Sales. | Prashant Mittal
Standard Process | Query Management Summary and Tracker | Automatic | Auto | Operations Head/CS Heads | Query Tracker Campaign wise to be made available in Zoho Projects itself for greater visibility of incoming requests and handling time etc promo wise. | CSM?Operations Head to review no Open queries are lying in system for their promos for more than 24 Hours. Respond and close the queries of the campaign | Any outbound request received from client to be checked in Estimate first and then discuss with CS Heads for next steps. | CS Heads/Operations Head
Aligning Marketing Team
Standard Process | Brief Marketing Team | Automatic | CS
| Marketing Collaterals | Automatic | CS
| Gathering Campaign Insights | Automatic | CS
| Campaign Closure with Marketing download of all data and documents. | Automatic | CS
Legal Requirements
Standard Process | Agreement Requirement | Automatic | CS | Prashant Mittal | Normal Zoho access of uploading documents etc. | Refer to CS Library for Agreement Copies
Campaign Invoicing/Billing
Standard Process | Invoice for the Campaign | Automatic | Auto | CS Heads/Prashant | Auto Task Creation tagged under JD's name basis payment terms closed in OB to be triggered. CSM can edit comment section to ammomodate nay client request on the same or nature of Invoice required. Possibility of taking inputs from Zoho Books against campaign wise tagging (Billed/Unbilled/Payment Received/Payment pending) | Details to be checked - PI/Tax Invoice as per the payment terms to be shared with client on timely basis for receiving payments ontime. | In case of any variation in CS Reconciliation vs Zoho to be flagged off imediatley to CS Heads. | CS Heads
Standard Process | Payment Followup | Automatic | Auto | NA | Auto reminders on all PI and Invoices raised to be received as Priority tasks in Zoho. | To be done basis Payment terms | Any delay to be reported immediately on Emails/ weekly huddles with PM/CS Heads and Sales
Standard Process | Marketing Collaterals | Automatic | Auto | CS Heads | Possibility of taking download of decription and attachments in a outside shared drive to be made possible. Summary of Monthly Campaigns wise collaterals shared by CSM and stored by Marketing to be shared with Super admin/CS Heads. | Pre-filled checklist and collaterals to be attached and uploaded on Zoho for Marketing Team. | No exceptions
Standard Process | Closure Deck | Manual | CSM | CS Heads | Simple Task closure with a pre-populated Closure deck format for reference purposes. | Just add on few slides on Go live deck with campaign statistics and insights received from client. Journey video also to be made before closure or future reference. No Project can be closed without submitting all details and receiving complete payments along with GST and Tax Certificates. | No exceptions
Other Exception Scenarios
Deviation 1 | Wastage Codes required |  | CSM | Prashant |  | Wastage Codes letter + (SO+OB) for extra codes(incase more than 2%) to be provided | Anything more than 2 % wastage codes need Prashants approval.
Deviation 2 | Campaign Extension |  | CSM | Prashant/Sales |  | Request to BD + Delivery head for commercials
Deviation 3.0 | Campaign Posponed |  | CSM | Prashant |  | Follow Campaign Postponed Checklist | Update FCM Update Ops Update MIS Team Update TnC
Deviation 3.1 | Campaign Postponed - Server + Account Management Charges |  | CSM | Prashant |  | SO to be generated for extra comercials incurred - Server + Account Management
Deviation 4.1 | Campaign Cancelled |  | CSM | Prashant |  | SO to be generated for comercials incurred - Server + Account Management + Print if any
Deviation 4.2 | Estimate/OB Cancellation |  | BD + Delivery Head | Sales/Prashant |  | OB to be changed/cancelled | Email approval required by Sales team and Prashant and get this done via Zoho CRM.